## Project List 2023
PROJECT ACTION DESCRIPTION January 2023 | PARTY / DEPT RESPONSIBLE | DATE TO BEGIN | ACTIONS REQUIRED | ACTION OUTCOME/DUE DATE | PRIORITY - High/Low/ Medium | ESTIMATE | ACTUAL COST | FINAL OUTCOME
Redevelopment of Children's Playground Surrounding Area | Pavilion Committee | 2023-03-01 | Fully landscape the play ground, as set out in new plan. Purchase new equipment and relocate existing as required. Develop and carry out a 5 year project plan. | It would be considered that this would be a 5 year plan as landscaping, removal of ash trees and planting of trees, plants and hedges would need a phased approach | High | Phase 1:- Hedgerow Planting around 2, thirds of the perimeter of the play area. (Contractor awarded - Muddy Boots) Est. £3,175 Phase 2:- New path to be laid as per the design provided by N. Baldwin. Budget £7,000 Estimates to be considered. Phase 3:- Continuation of fence to replace dangerous barbed wire on 1/3 of the play park to be completed. Estimate: £3500 Phase 4:- Phase 5:- |  | Phase 1 Completed
Sustainability Project | Cllrs. Phil Oram/Sam Jordan/Nickey Turner | In progress | Regular meetings to be convened to establish terms of reference. | Purchase of a Thermal Imaging Camera | High | Grant awarded for the purchase of the Thermal Imaging Camera from Winchester City Council | Grant awarded
Memorial garden, Orchard / allotments | Cllr. June Perrins | Awaiting update from MOD | Locate suitable acre-age of land (2acres) £22,000.00 + Orchard Development Costs) | Pursue with Defence Miniter and local MP - April 2023 | High | Based on agricultural cost, 3 acres estimate 33k, Water Installation 3K - 5 K. Estimate 50K, Orchard Development costs to be added.
Review of road signage and free standing signage, re-engining of ditch. | Cllr. June Perrins Cllr. Lohani Cllr. John Berry |  | Contact Landowner to seek approval/Estimate costs of providing the path/Declined by land owner. Research alternatives. Contact landowner with a view to puchase of 2 acres of land. | Landowner has declined our request for a permissive path. Referred matter to HCC Transport Team to review signage and the filling in of the ditch widening the margin, previous cost estimate would be 60K. Signage review, installation of pinch point. | High | Estimate received previously 60k + 11k for surveying with regard to ditch engineering, signage., awaiting estimate for pinch-point. | Permission refused by Landowner for permissive path. New plans to improve road signage and management being developed by the Strategic Planning Team April 2023. Village sign and pinchpoint to be considered.
Village Signage | Cllr June Perrins |  | Village signage and posts to be positioned in Alresford Drove to help slow traffic flow | Appropriate signage and posts located awaiting costs related to installation | High | Estimate £8000 - CIL funds to be used for overall cost. | Awaiting response from Highways - Previous agreement to have the new sign and gateway now linked to the overall review of Alresford Drove
Medium | Pavilion Committee |  | Fell diseased Ash | Ash Trees will only be felled when absolutely necessary. A staged approach over years | High | Await new estimate
New sign for Long Barrow Site | Cllr. Ann Peal |  | New Print needs to be arranged to replace the present very weathered sign | Contact WCC Archaeology Dept. | Low | Cllr. Peal liaising with the Archeology Team |  | Work in progress
Lighting in Downs Road | Parish Council - Decision | 2019-10-01 | Provision of LED lighting - 32 units. | Parish Council to review suggestion and make recommendations | Low | Estimate £12,00.00 |  | Under reveiw
Estimates received at present time 17th April, 2023:- £135,674.00. Please note that the playpark project is ongoing and phased costs will be added when completed, as will actuals when other are projects completed.