## Project List 2023
PROJECT ACTION DESCRIPTION April 2024 | PARTY / DEPT RESPONSIBLE | DATE TO BEGIN | ACTIONS REQUIRED | ACTION OUTCOME/DUE DATE | PRIORITY - High/Low/ Medium | ESTIMATE | ACTUAL COST | FINAL OUTCOME
Redevelopment of Children's Playground Surrounding Area | Pavilion and Recreation GroundCommittee | 2023-03-01 | Fully landscape the play ground, as set out in new plan. Purchase new equipment and relocate existing as required. Develop and carry out a 5 year project plan. | It would be considered that this would be a 5 year plan phased approach, new fencing where needed, landscaping, removal of ash trees and replanting of new trees. Hedges, installation of new equipment and renovation of existing where needed. | High | Phase 1:- Hedgerow Planting around 2, thirds of the perimeter of the play area. (Contractor awarded - Muddy Boots) Est. £3,175 Phase 2:- Continuation of fence to replace dangerous barbed wire on 1/3 of the play park to be completed. Estimate: £3500 Phase 3:- New path and tree line to be installed as per the design provided by N. Baldwin. Budget £11,000 3 Estimates to be considered. *Ash dieback trees removed and new trees installed. | Phase 1 £3,157 Phase 2 £3,820 Phase 3 - £11,633 +£800 | Phase 1, 2 and 3 Completed
Playground upgrade (part of the redevelopment plan above) | Pavilion and Recreation Ground Committee | 2024-05-01 | To review existing equipment and decide on replacement strategy for certain units. | To seek the required number of quotations related to each chosen item, onace achieved move to decision making process | High | Phase 3:- 3 quotes have been obtained for each unit and decisions have been made in terms of the following units being chosen. * Tractor Unit * 360 degree swing *Refurbishment of the Vintage Horse | Est £34000
Pavilion Refurbishment | Pavilion and Recreation Ground Committee | Completed | Replace exterior doors with new metal doors and metal frames (required due to weathering and wear) | Contractor contacted to obtain specification of the doors. Work Now completed | High | Await quotation/costs to be allocated to Pavilion reserve accummulated for this purpose. Average estimate £8500 | 8094 | Completed
Sustainability Project | Cllrs. Phil Oram/Sam Jordan/Nickey Turner | Completed | Regular meetings to be convened to establish terms of reference. | Purchase of a Thermal Imaging Camera | High | Grant awarded for the purchase of the Thermal Imaging Camera from Winchester City Council | Grant awarded £1000 | Completed
Highways Safety Improvements on Down Road | Cllr. Grish Lohani | Completed | Traffic Safety Measures to be impleted in the vicinty of the School entrance | Hampshire County Council traffic scheme to approve schedule of works | High | Costs to be shared between CFI funds and Parish Council CIL | 13917
Memorial garden, Orchard / allotments | Cllr. June Perrins Rachael Jones | Awaiting final update from Steve Brine MP Await update from BCM land agent | Locate suitable acre-age of agricultural land (3acres) £36,000.00 + Orchard Development Costs) | Pursue with Defence Miniter and local MP - April 2024 - (Not considered a viable option). BCM Land Agent to contact Defence Infrastructure Organisation to pursue sale opportunity | High | Based on agricultural cost, 3 acres estimate 33k, Water Installation 3K - 5 K. Estimate 75K, Orchard Development costs to be added. | Estimate 111k
Village Signage | Cllr June Perrins | 2023-12-01 | Village signage and posts to be positioned in Alresford Drove to help slow traffic flow | Appropriate signage and posts located awaiting costs related to installation | High | Estimate £3k - CIL funds to be used for large % of cost. CFI of £700 to be awarded to overall cost | 2500 | Paid £1,250 to date
Ash Dieback | Pavilion Committee | 2024-05-01 | Fell diseased Ash | Ash Trees will only be felled when absolutely necessary. A staged approach over years | High | Remove Ash Trees as needed and replace with new Trees (Estuimate £1000 per tree) | 1650
Fencing Upgrade | Pavilion and Recreation GroundCommittee | 2024-01-01 | Pavilion new fencing required around Astro Turf | Design agreed move to next phase. Quotes to be reviewed | High | Estimate 2K
Water Fountain | Pavilion and Recreation GroundCommittee | 2024-01-01 | Installation of Exterior Water fountain | Design agreed move to next phase | Medium | 3 quotations now received to be reviewed at next Pavilion Meeting. Quotation chosen | 6000 | Item Purchased, needs to be installed
Pump Track | Pavilion and Recreation Ground Committee | 2023-12-01 | Obtain 3 quotes and review | The Pump Track would replace the overgrown and unusable BMX track. | Medium | Estimate £100k (Grant funding to be sought)